## Slide 1
Guiding Framework for Platform Disposition
Six principles, applied in order, decide the next best action for every BOBJ report. The first principle a report matches sets its disposition; only what survives all six is scored.
INPUTS
CONSIDERATIONS USED — GUIDING PRINCIPLES, APPLIED IN ORDER
DISPOSITION
1
BOBJ metadata & audit trail
Run counts, last-run dates, schedules and publication lists over 18 months
2
Report profile
Source data, visualisation, interaction mode, audience and latency
3
Semantic complexity
Query complexity from join count, universe contexts, metrics and aggregate awareness
4
Code repository
Table and view DDLs, stored procedures and packages, including Epic custom-schema objects
5
Architecture & data flow
Current Oracle lineage and the target Cogito, SQL Server and Databricks mapping
6
Asset owners & support teams
Business criticality, regulatory drivers, known defects and rebuild appetite
1. Prove it is still used
Read 18 months of run history from the BOBJ audit trail. Check for a legal hold or a regulatory driver. Retire the report when nobody runs it and nothing requires it.
▸ Retire
2. Collapse the duplicates
Compare Report DNA signatures across the estate. Name one survivor for each duplicate group. Redirect the other consumers to it and retire the copies.
▸ Consolidate
3. Keep clinical work inside Epic
Ask where the report is consumed and what data it reads. Send it to Cogito when it runs on Epic data and drives action inside the clinical workflow.
▸ CogitoSQL
4. Honour the format obligations
Flag statutory layouts, pixel-exact output and scheduled PDF bursts. Rebuild these as Paginated Reports, which reproduce the layout Crystal delivered.
▸ Power BI Paginated
5. Settle the custom schema before the report
Trace every Epic custom object the report reads. Decide one of three outcomes for each: re-derive it from Clarity or Caboodle, re-home it to Delta, or retire it together with the reports that depend on it. Move the report only once its data has a home.
▸ Report disposition follows the data decision
6. Score what survives — the platform fit scorecard
Score every remaining report on four weighted groups: Data Gravity 20 — where its data will live once Oracle is gone; Consumption Pattern 30 — who uses the report and how they use it; Rebuild Feasibility 25 — what it costs to recreate the logic; Runtime & Control 25 — what the target platform must enforce at run time.
Assign the platform that takes 60% or more of the weighted points. Split the report into two assets when the points split, rather than forcing a compromise platform. Break ties toward the platform that removes the most BOBJ universes and jobs in this wave. Escalate to the retain exception only when nothing reaches 60%.
Seven scored dimensions sit behind the four groups — detail on the Platform Fit Scorecard.
▸ CogitoSQL · Power BI · Databricks AI/BI
CogitoSQL
Rearchitect. Rebuild in Reporting Workbench, Radar or SlicerDicer on Clarity and Caboodle.
Reached from principle 3, or a Data Gravity plus in-workflow score
Power BI
Rearchitect. Build a curated semantic model; use Paginated Reports for statutory and bursted output.
Reached from principle 4, or a Consumption plus Format score
Databricks AI/BI
Replatform. Land the data in Delta, then rebuild as AI/BI dashboards with Genie for exploration.
Reached from principle 5, or a Data Gravity plus ad-hoc score
Retire / Consolidate
Run as-is to a fixed retirement date. Redirect consumers to the surviving asset, then decommission.
Reached from principles 1 and 2 — never scored
Retain in BOBJ — exception
Keep only when all four hold: rebuild over 40 hours, no equivalent this wave, named owner accepts, universe survives the Oracle exit. Set a sunset date.
Escalation from principle 6 only
HIPAA checkpoint — clear it at every principle, not at go-live. Document the security-model translation before any asset moves: map BOBJ universe restrictions to Unity Catalog row filters and column masks, or to Power BI semantic-model RLS. Audit every BOBJ publication that emails PHI to a distribution list. Scope Databricks Genie spaces to curated gold tables only, never to raw custom-schema extracts. Confirm state record-retention obligations before deleting the output of any retired report.
Principles are applied in order and the first match decides — a report that exits at principle 1 or 2 is never scored. Usage evidence draws on the BOBJ CMS audit trail over a rolling 18 months; a 90-day window understates quarterly and annual regulatory reporting.
Notes: How to walk this slide: Left — the six evidence sources we collect per report. Nothing in the middle column can be applied without them; input 1 (usage) and input 4 (code repository) do most of the work. Middle — six principles applied in order. The first one a report matches decides its disposition, so most of the estate never reaches scoring. Expect 30-45% to exit at principles 1 and 2. Principle 5 is the pivot for this client: the Epic custom schema is a data decision wearing a report-disposition costume. Decide per custom object whether it is redundant with Caboodle, genuinely bespoke and headed for Delta, or orphaned. The report follows the data. Principle 6 is the scorecard, condensed. Four weighted groups totalling 100 points; a 60% concentration in one platform column is a clean call. Right — five dispositions. Retain in BOBJ is drawn as an exception on purpose: four criteria must all hold and a sunset date is mandatory. If the retain bucket exceeds ~10% of the estate, the criteria are too soft. Forcing function: the Oracle decommission date caps the retain bucket. If a universe dies with Oracle, retention is not an available option.

## Slide 2
Platform Fit Scorecard — the Seven Dimensions Behind the Four Groups
Applied only to reports that reach principle 6. The four groups on the rubric are rollups of these seven scored dimensions: Data Gravity 20 = Data source · Consumption Pattern 30 = Audience 15 + Interaction mode 15 · Rebuild Feasibility 25 = Semantic complexity 15 + Format fidelity 10 · Runtime & Control 25 = Latency 10 + Governance & RLS 15.
Rubric group | Scored dimension | Wt | CogitoSQL favoured when… | Power BI favoured when… | Databricks AI/BI favoured when… | Retain signal (diagnostic only)
Data Gravity 20 pts | Data source | 20 | Clarity / Caboodle-native; Epic-delivered content already covers the model | Curated SQL Server gold layer or mart reachable through the gateway | Lakehouse-native, multi-source, high volume, or re-homed custom schema | Universe still bound to Oracle objects with no re-platform target defined
Consumption Pattern 30 pts | Audience | 15 | Clinicians and unit operations working inside Hyperspace | Executives and broad enterprise distribution | Analysts and data science running their own exploration | A small legacy user pocket with no growth and no owner
 | Interaction mode | 15 | Worklist, in-context lookup, patient-level action | Curated dashboards, mobile, scheduled subscriptions | Ad-hoc exploration, Genie natural-language query, notebook-adjacent | Static scheduled output that nobody interacts with
Rebuild Feasibility 25 pts | Semantic complexity | 15 | Epic-delivered content, or a thin custom layer over it | Rebuildable as a Power BI semantic model within the wave | Expressible as SQL or Unity Catalog metric views | Deep universe logic — contexts, aggregate awareness — with nobody able to rebuild it
 | Format fidelity | 10 | Low — operational lists and worklists | High — Paginated Reports absorb statutory and bursted layouts | Low to medium — analytic canvas, exportable | Crystal-grade pixel fidelity that Paginated genuinely cannot reach
Runtime & Control 25 pts | Latency | 10 | Near-real-time from Chronicles via Reporting Workbench | Hourly or daily refresh is acceptable to the consumer | Streaming-to-batch on Delta with incremental refresh | Overnight batch only, with no latency pressure at all
 | Governance & RLS | 15 | Epic security classes inherit automatically | Entra-driven RLS enforced on the semantic model | Unity Catalog row filters, column masks, lineage and full audit | Undocumented universe security nobody owns — a liability, not a justification
Planning heuristic for an Epic-based BOBJ estate
30–45% retire or consolidate · 15–25% CogitoSQL · 20–30% Power BI including paginated · 10–20% Databricks AI/BI · under 10% time-boxed retain
If the retain bucket lands above 10% after scoring, the exception criteria are too soft — tighten the rebuild-hours ceiling, or accept L2 rather than L3 equivalence for low-criticality reports. The Oracle decommission date is the hard ceiling on the whole bucket.
Weights sum to 100 and are tuned to a BOBJ-reduction objective; re-weight Data Gravity upward if the Oracle exit date compresses, or Rebuild Feasibility upward if analyst capacity rather than runway is the binding constraint.
Notes: Backup detail behind principle 6 on the rubric slide. Use it when a stakeholder challenges a specific disposition — walk the dimension, not the conclusion. The retain column is deliberately framed as a diagnostic: every cell describes a condition to remediate rather than a platform virtue. Undocumented universe security in particular is a compliance liability the client already carries, and migration is the opportunity to close it. Re-weighting guidance: Data Gravity up if the Oracle exit compresses; Rebuild Feasibility up if analyst capacity is the binding constraint rather than runway.

## Slide 3
Sequential Activities by Disposition
Each disposition carries its own six-step runbook, executed only after the rubric has set the path. Every step carries an exit criterion, so progress is evidenced rather than asserted. Every path ends by removing the BOBJ object; the exception path ends at a dated sunset.
DISPOSITION
STEP 1
STEP 2
STEP 3
STEP 4
STEP 5
STEP 6
CogitoSQL
Rearchitect
Confirm Epic-native fit
Verify every data element exists in Clarity or Caboodle. Flag any custom-schema gap.
Exit: Gap list signed by the Cogito lead
Pick the Epic tool
Choose Reporting Workbench, Radar, SlicerDicer or a governed Cogito SQL view.
Exit: Tool decision in the asset record
Translate the security
Map universe restrictions onto Epic security classes and template security.
Exit: Mapping reviewed by Epic security
Build in non-prod
Configure the template. Peer-review it against the source report specification.
Exit: Build peer-reviewed in non-prod
Prove equivalence
Reconcile rows and totals to L2+. Run clinician UAT inside Hyperspace context.
Exit: Reconciliation pack and UAT sign-off
Release and retire
Publish to the release, redirect users, disable schedules, decommission the object.
Exit: BOBJ object deleted, schedules off
Power BI
Rearchitect
Split the workload
Decide interactive semantic model, Paginated Report, or both from one dataset.
Exit: Workload split recorded per artifact
Certify the dataset
Model the gold-layer tables, define measures, certify the semantic model.
Exit: Semantic model marked certified
Rebuild the artifact
Recreate the visuals, or reproduce the statutory layout in Paginated Reports.
Exit: Artifact built and peer-reviewed
Wire RLS and delivery
Set Entra roles, sensitivity labels and subscriptions replacing BOBJ publications.
Exit: RLS tested with a non-privileged account
Prove equivalence
Reconcile the data, check layout fidelity, run a full subscription burst test.
Exit: Reconciliation and burst-test evidence
Release and retire
Deploy through the workspace pipeline, redirect users, decommission the object.
Exit: BOBJ object deleted, publications off
Databricks AI/BI
Replatform
Land the source
Ingest the Oracle and Epic custom-schema objects into bronze via CDC or batch.
Exit: Bronze feed running and monitored
Model up to gold
Rebuild the universe logic as Delta tables and Unity Catalog metric views.
Exit: Gold tables and metric views published
Apply the governance
Set UC row filters, column masks, lineage capture and audit logging.
Exit: UC policies applied, audit logging on
Build the dashboard
Recreate the visuals. Scope a Genie space to gold tables with curated instructions.
Exit: Dashboard and Genie space reviewed
Prove equivalence
Reconcile to BOBJ output. Test Genie against a known-answer question set.
Exit: Reconciliation and Genie test results
Release and retire
Grant through UC groups, redirect users, retire the object and the Oracle feed.
Exit: BOBJ object deleted, Oracle feed off
Retire / Consolidate
Run down
Document the evidence
Record the 18-month usage finding, or the duplicate class and its survivor.
Exit: Evidence attached to the asset record
Notify the consumers
Give 30 days' notice to last-known users and the asset owner. Log objections.
Exit: Notice sent, objection window closed
Redirect to the survivor
Point consumers at the canonical asset and confirm it meets their need.
Exit: Consumers confirmed on the survivor
Preserve the record
Archive the final output and definition where state retention rules apply.
Exit: Archive stored with its retention basis
Disable, do not delete
Stop schedules, remove from folders, quarantine the object for 60–90 days.
Exit: Quarantine start date logged
Decommission
Delete object, unshared universe and connection. Update the asset inventory.
Exit: Inventory updated, object gone
Retain in BOBJ
Exception
Document the exception
Record which of the four criteria hold, with the evidence attached to each.
Exit: Criteria evidence attached
Secure the sign-off
Have named business and platform owners accept, then register the exception.
Exit: Exception registered with both owners
Set the sunset date
Bound it by the Oracle decommission milestone and enter it in the wave plan.
Exit: Sunset date entered in the wave plan
Re-point the source
Move the universe to SQL Server or Databricks. If it cannot move, retention is void.
Exit: Universe re-pointed off Oracle
Freeze the asset
Block enhancements. Any change re-enters the rubric at principle 1.
Exit: Change freeze applied to the asset
Review at every gate
Re-test against the rubric each wave. Force a disposition at the sunset date.
Exit: Wave review logged, sunset tracked
HIPAA checkpoint — clear it at step 5 of every path. Complete the security-model translation and the PHI-scope review before release, then re-test row-level access with a non-privileged account rather than an admin. Do not carry BOBJ publication recipient lists into Power BI subscriptions or Unity Catalog groups without re-validating each recipient's minimum-necessary basis. On the retire path, confirm the retention obligation at step 4 before anything is deleted at step 6.
Steps run in order and step 6 is not optional — a report is not migrated until the BOBJ object, its universe if unshared, and its schedules are gone. Track step 6 completion, not step 5, as the measure of BOBJ reduction.
Notes: This is the execution layer under the rubric — the rubric picks the lane, this slide is what the delivery team does in it. Three points to land: 1) The paths are genuinely different. A Cogito rebuild and a Databricks replatform share almost no activities, which is why a single generic migration plan fails on this programme. 2) Step 5 is the same idea everywhere — prove equivalence before release — but the evidence differs: clinician UAT in Hyperspace for Cogito, layout fidelity and burst tests for Paginated, a known-answer question set for Genie. 3) Step 6 is the one that actually reduces BOBJ. Programmes routinely report 'migrated' at step 5 and leave the original running in parallel for a year. Track step 6. Retire path watch-out: step 5 (disable, do not delete) exists because reversal requests almost always arrive within the first two months. A 60-90 day quarantine costs nothing and avoids a rebuild. Retain path watch-out: step 4 is the kill switch. If the universe cannot be re-pointed off Oracle, the exception is void and the report is forced back into the rubric.

## Slide 4
Report Migration Approach — Steps by Target Platform
Migration activities only — retire and consolidate sit outside this view. Power BI and Databricks each carry two tracks: the Oracle database objects the report reads, then the report itself. The data track must clear a step before the report track can clear the same step. CogitoSQL has no data track, because it reads Epic-managed Clarity and Caboodle.
MIGRATION TRACK
1 · ASSESS
2 · DESIGN
3 · BUILD
4 · SECURE
5 · VALIDATE
6 · CUT OVER
CogitoSQL
Report rebuild
Rearchitect
Confirm Epic coverage
Check every element exists in Clarity or Caboodle. Route gaps to Databricks.
Exit: Coverage confirmed, gaps routed
Select and spec the tool
Choose Reporting Workbench, Radar, SlicerDicer or a Cogito SQL view.
Exit: Build spec approved
Build in non-production
Configure the template. Peer-review against the source report spec.
Exit: Peer-reviewed in non-prod
Apply Epic security
Map universe restrictions to security classes and template security.
Exit: Signed by Epic security
Reconcile and run UAT
Reconcile rows and totals to L2+. Run clinician UAT in Hyperspace.
Exit: Reconciliation pack and UAT
Release and delete source
Publish, redirect users, disable schedules, delete the BOBJ object.
Exit: BOBJ deleted, schedules off
Power BI
Data objects
Oracle → MS SQL Server
Inventory the objects
List every table, view, materialized view, procedure and package read.
Exit: Object dependency list published
Map types to SQL Server
Table to table, view to view, MV to indexed view, PL/SQL to T-SQL.
Exit: Mapping approved per type
Convert and deploy
Migrate DDL and data, rewrite PL/SQL as T-SQL, build the gold schema.
Exit: Deployed in the gold schema
Secure the SQL schema
Set schema roles and least privilege, mask PHI columns, enable audit.
Exit: Roles, masking and audit on
Reconcile to Oracle
Row counts, checksums, key reconciliation. Re-run procs, compare output.
Exit: Reconciliation signed per object
Retire the Oracle object
Repoint consumers, freeze the Oracle object, drop it at the wave gate.
Exit: Oracle object dropped
Power BI
Report rebuild
Rearchitect
Decide the artifact split
Decide semantic model, Paginated Report, or both from one dataset.
Exit: Artifact split recorded
Model and certify dataset
Model on the SQL Server gold schema, define measures, certify it.
Exit: Semantic model certified
Rebuild the artifact
Recreate visuals on the model, or rebuild the layout in Paginated.
Exit: Built and peer-reviewed
Wire RLS and delivery
Set Entra roles, RLS, sensitivity labels and subscriptions.
Exit: RLS tested, non-privileged
Reconcile and test
Reconcile the report, check layout fidelity, run a burst test.
Exit: Reconciliation and burst test
Deploy and delete source
Deploy through the pipeline, redirect users, delete the BOBJ object.
Exit: BOBJ deleted, publications off
Databricks
Data objects
Oracle → Delta + UC
Inventory the objects
Parse universe SQL. List every table, view, MV, procedure and package.
Exit: Dependency graph published
Map types to Databricks
Table to Delta, view to SQL view, MV to Delta MV, PL/SQL to UDF or DLT.
Exit: Mapping approved per type
Land, convert and deploy
Ingest to bronze, build silver and gold, deploy views and logic into UC.
Exit: Objects deployed in the catalog
Govern in Unity Catalog
Set ownership, row filters, column masks, lineage. Register PHI objects.
Exit: UC policies and audit logging on
Reconcile to Oracle
Row counts, checksums, key reconciliation. Compare re-run output.
Exit: Reconciliation signed per object
Retire the Oracle object
Repoint consumers, freeze the object, drop it at the wave gate.
Exit: Oracle dropped, lineage updated
Databricks AI/BI
Report rebuild
Replatform
Confirm the gold layer
Verify the objects this report needs are landed and certified above.
Exit: Gold tables available
Rebuild the semantics
Express the universe logic as SQL views or UC metric views.
Exit: Metric views published
Build the dashboard
Recreate the visuals as an AI/BI dashboard. Scope a Genie space.
Exit: Dashboard and Genie reviewed
Grant through UC
Bind UC groups, inherit row filters and masks, switch on audit.
Exit: UC grants applied, audit on
Reconcile and test Genie
Reconcile to BOBJ output. Run a known-answer set through Genie.
Exit: Reconciliation and Genie results
Release and delete source
Grant to UC groups, redirect users, delete the object and Oracle feed.
Exit: BOBJ deleted, Oracle feed off
Retain in BOBJ
Re-point and freeze
Exception
Record the exception
Capture which of the four criteria hold, with evidence attached.
Exit: Criteria evidence attached
Plan the re-point
Choose the target connection, set the sunset date, agree the freeze.
Exit: Re-point plan and sunset agreed
Re-point the universe
Move the connection to SQL Server or Databricks, or retention is void.
Exit: Re-pointed off Oracle
Re-test the restrictions
Confirm universe restrictions still enforce after the change.
Exit: Restrictions re-tested
Reconcile either side
Compare output either side of the re-point. No logic drift.
Exit: Pre and post reconciliation
Freeze and track sunset
Block enhancements, register the exception, re-test each wave.
Exit: Sunset in plan, freeze applied
Oracle → MS SQL Server (feeds Power BI)
Table → table with clustered index · View → view, or indexed view where the report needs it · Materialized view → indexed view, or a scheduled table where refresh cost is high · Stored procedure → T-SQL stored procedure · Package → schema-bound procedure set sharing one header
Oracle → Databricks (feeds Databricks AI/BI)
Table → managed Delta table · View → Databricks SQL view · Materialized view → Delta materialized view, or a scheduled gold table · Stored procedure → SQL UDF for set logic, notebook or DLT pipeline for procedural logic · Package → notebook module or Python wheel in Unity Catalog
HIPAA checkpoint — clear it at steps 4 and 5 of every track. Re-assert minimum necessary as objects land: PHI columns are masked and row-level access enforced in SQL Server and in Unity Catalog before any report is pointed at them. Re-test with a non-privileged account, never an admin. Do not carry BOBJ publication recipient lists into Power BI subscriptions or UC groups without re-validating each recipient. A universe re-pointed under the retain exception must have its restrictions re-tested — a connection change silently breaks row-level security.
Notes: Structural change from the previous version: the database-object work no longer sits in its own lane. It now sits inside the platform it feeds, because the data target follows the report target. Power BI reports are served from MS SQL Server, so their Oracle objects convert to SQL Server: tables, views, indexed views and T-SQL stored procedures. Databricks AI/BI reports are served from the lakehouse, so their objects convert to Delta and Unity Catalog. CogitoSQL has no data track at all — it reads Clarity and Caboodle, which Epic maintains. If a Cogito candidate turns out to need custom-schema data, it is not a Cogito candidate; step 1 routes it to the Databricks lane. Sequencing rule inside each pair: the data track must clear a step before the report track clears the same step. Reconcile the data before reconciling the report, or you will chase report variances that are really data variances. Effort concentration: tables and views convert close to mechanically on both targets. Materialized views, PL/SQL stored procedures and packages are where the schedule risk sits, because neither target has a like-for-like construct — each one is a design decision, not a conversion. Size that population before committing to a wave plan. Consequence worth raising with the client: an object read by both a Power BI report and a Databricks report gets built twice, on two platforms. Either accept the duplication or decide a single system of record per object before phase 2 dispositions are finalised.

## Slide 5
Report Migration — Parallel Execution Paths
Disposition is already assigned. All four platform paths run concurrently — nothing waits on another platform. Two are gated by a database migration: the Oracle objects a Power BI report reads move to MS SQL Server, and those a Databricks report reads move to Delta and Unity Catalog. CogitoSQL needs none.
Disposition register (input, not an activity)
CogitoSQL — Rearchitect
1A. Confirm Epic coverage in Clarity and Caboodle
1B. Select and spec the Epic tool
1C. Build the template in non-production
1D. Apply Epic security classes
1E. Reconcile to L2+ and run clinician UAT
1F. Release and delete the BOBJ object
Power BI · database objects → MS SQL Server
2A. Inventory tables, views, MVs, procedures, packages
2B. Map each object type to a SQL Server target
2C. Migrate DDL and data, rewrite PL/SQL as T-SQL
2D. Set schema roles and mask PHI columns
2E. Reconcile counts, checksums and procedure output
2F. Freeze and drop the Oracle object
Power BI — Rearchitect
3A. Decide the artifact split
3B. Model and certify the dataset
3C. Rebuild the report or the paginated layout
3D. Wire Entra RLS, labels and subscriptions
3E. Reconcile the report and run a burst test
3F. Deploy and delete the BOBJ object
Databricks · database objects → Delta and Unity Catalog
4A. Parse universe SQL and inventory the objects
4B. Map each object type to a Databricks target
4C. Land to bronze, build gold, deploy views and logic
4D. Apply UC row filters, masks and lineage
4E. Reconcile counts, checksums and re-run output
4F. Freeze and drop the Oracle object
Databricks AI/BI — Replatform
5A. Confirm the gold layer is ready
5B. Rebuild the semantics as metric views
5C. Build the dashboard and Genie space
5D. Grant through Unity Catalog groups
5E. Reconcile to BOBJ output and test Genie
5F. Release and delete the BOBJ object
Retain in BOBJ — Exception
6A. Record which exception criteria hold
6B. Plan the re-point and set the sunset
6C. Re-point the universe off Oracle
6D. Re-test the universe restrictions
6E. Reconcile either side of the re-point
6F. Freeze and track to the sunset date
Parallel by design. The four platform paths run at the same time; none waits on another. Capacity, not sequence, sets the wave size. Shaded tracks are database migrations, needed only where the report reads Oracle custom-schema objects — CogitoSQL reads Epic-managed Clarity and Caboodle and has none. Dotted link is a gate: a report track cannot clear step E until the database track above it has, so data variances surface before report variances. Step F is the decommission milestone on every path — the point at which the reduction is actually booked.
HIPAA checkpoint — steps D and E on every path. PHI columns are masked and row-level access enforced in SQL Server and Unity Catalog before any report is pointed at them. Re-test with a non-privileged account, never an admin. Do not carry BOBJ publication recipient lists into Power BI subscriptions or UC groups without re-validating each recipient. Under the retain exception, a re-pointed universe must have its restrictions re-tested — a connection change silently breaks row-level security.
Notes: Execution view. Mobilisation and disposition are assumed complete — this slide starts from the disposition register. Headline: the four platform paths are independent of each other and run concurrently. What limits throughput is delivery capacity per platform, not sequence between platforms. Size waves by the scarcest skill, which on this programme is usually the PL/SQL-to-target conversion capability, not report developers. The two shaded tracks are the database migrations. They exist only for Power BI and Databricks; CogitoSQL reads Clarity and Caboodle, which Epic maintains. The dotted gate is the one hard dependency on the slide: a report cannot clear step E (validate) until its database track has cleared step E. Break that rule and the team spends the programme chasing report variances that are really data variances. Effort concentration inside steps 2C and 4C: tables and views convert close to mechanically. Materialized views, PL/SQL stored procedures and packages have no like-for-like construct on either target, so each is a design decision. Size that population before committing to a wave plan. Duplication to decide early: an object read by both a Power BI report and a Databricks report is built twice, on two targets. Either accept it or nominate a single system of record per object.

## Slide 6
Accelerating the Migration — Agents by Phase
Twelve Data Assist accelerators cover Assess, Design, Build and Validate on every disposition path. Secure and Cut over are out of scope in this view and stay manual. ★ marks a new accelerator.
Report Rationalization
Migration Phase
Rationalization Agents
Migration Agents
Validation & Tuning Agents
1
Report Rationalization & Disposition
DRECT · Rationalizer · ★ Fit Scorer
2
★ Schema Mapper
classify · map · size the effort
3
DDL & Object Converter
Code Converter · Data Migration Agent
4
Report Migration Agents
Automator · Transpiler · ★ AI/BI Gen
5
Testing Agents: Data & Reports
CATE · Automated Report Tester
6
Code Optimization Agent
post-migration query tuning
Data Assist DRECT · Report Rationalizer · ★ Platform Fit Scorer · ★ Schema Mapper · Deloitte Code Converter · Data Migration Agent · Report Automator · Epic Oracle-to-SQL Transpiler · ★ AI/BI Dashboard Generator · CATE Test Engine · Automated Report Tester · Code Optimizer
Classify every Oracle object the surviving reports read and map it to its MS SQL Server or Delta target.
Convert table and view DDL, materialized views, packages and stored procedures, then move history and incremental data.
Rebuild each report on the platform its disposition assigned — Power BI, Cogito, or Databricks AI/BI with a scoped Genie space.
Reconcile migrated objects for row count, checksums and keys, then validate rebuilt reports against the BOBJ baseline.
Lifecycle coverage in this view
ASSESS
Rationalization & Disposition
DESIGN
Schema Mapper · Fit Scorer
BUILD
Converters · Migration Agents
SECURE
out of scope — manual
VALIDATE
Testing Agents · CATE
CUT OVER
out of scope — manual
Scope of this view. Secure and Cut over are deliberately excluded here, but they are not optional work — the earlier coverage audit found zero of six activities automated in each. Secure carries the HIPAA exposure on every path, and Cut over is the step that actually removes the BOBJ estate, so a programme that automates only the four steps above will build faster than it reduces.
HIPAA checkpoint. Every agent runs inside the secured environment on the same PHI boundary as the pipeline — no report output, universe extract or reconciliation sample leaves it. Reconciliation samples drawn by CATE and the Automated Report Tester contain PHI and are treated as production data, not test data. Agents propose; the data owner still approves.
1
Report Rationalization & Disposition
DRECT · Report Rationalizer · ★ Platform Fit Scorer
Reverse-engineers universe SQL and report queries into an object dependency graph and lineage. Mines 18 months of CMS run history and Report DNA signatures for dormancy and duplicate classes. Scores each surviving report against the rubric and publishes the disposition register.
2
★ Schema Mapper
Classifies every Oracle custom-schema object a surviving report reads — table, view, materialized view, stored procedure, package — maps each to its MS SQL Server or Delta and Unity Catalog target, and sizes the conversion effort per object.
3
DDL & Object Converter
Deloitte Code Converter · Data Migration Agent
Converts table and view DDL, materialized views, packages and stored procedures into T-SQL or Delta and Unity Catalog constructs, then generates the history and incremental load configuration to move the data.
4
Report Migration Agents
Report Automator · Epic Oracle-to-SQL Transpiler · ★ AI/BI Dashboard Generator
Rebuilds each BO report on the platform its disposition assigned: a Power BI semantic model or paginated layout, a Cogito Reporting Workbench template or SQL view, or a Databricks AI/BI dashboard with a Genie space scoped to governed gold tables.
5
Testing Agents: Data & Reports
CATE Test Engine · Automated Report Tester
Reconciles row counts, checksums, business keys and re-run procedure output against Oracle, then compares report output, layout fidelity, burst delivery and Genie answers against the BOBJ baseline.
6
Code Optimization Agent
Monitors query behaviour on SQL Server and Databricks after migration and recommends tuning for performance and cost, including partitioning, clustering and refresh strategy.
Notes: Same accelerator content as the coverage slide, redrawn as the agent flow the client already recognises. Deliberately scoped to Assess, Design, Build and Validate. Secure and Cut over are shown greyed on the lifecycle strip rather than omitted, because dropping them silently would misrepresent the coverage audit — each had zero of six activities automated. Two accelerators are new to this programme and marked with a star: the Platform Fit Scorer, which applies the disposition rubric, and the AI/BI Dashboard Generator, which serves Databricks. The Schema Mapper is also new and closes the Design step. Point to make at box 2: the Schema Mapper is where the schedule risk is sized. Tables and views convert close to mechanically; materialized views, PL/SQL procedures and packages have no like-for-like construct on either target, so each is a design decision. Watch-out for the room: this slide shows agents doing work, but every conversion still lands in a human review gate. Nothing here approves its own output.